RITUAL & STONE

Luxury Bathroom Design Studio

Business Action Plan

Your roadmap from foundation to freedom

Prepared for Ced — June 2026

# 1. The Bones

Everything that must exist before you serve your first paying client. These are not optional admin tasks — they are the infrastructure of a professional business. Do these in June 2026, in roughly this order.

## 1.1  Legal & Administrative Foundation

None of these take long. Most can be done in a single Monday morning. Get them done first so everything else is built on solid ground.

- ABN first. Register your business name

- Confirm you have an active ABN (apply at abr.business.gov.au if not — free, takes minutes)

- Search ASIC for ‘Ritual and Stone’ availability (asic.gov.au) — registration is ~$39 for 1 year

- Check IP Australia for trademark conflicts (ipaustralia.gov.au) — search before you invest further

- Domains & handles. Secure your digital identity

- Register ritualandstone.com.au (recommended) and ritualandstone.com as a backup

- Secure @ritualandstone on Instagram and Pinterest now — even if you won’t post yet

- Professionalism from day one. Get a business email address

- hello@ritualandstone.com.au (or ced@ritualandstone.com.au) via Google Workspace ($10-14/month)

- This email goes on everything — intake forms, invoices, correspondence

- Keep money clean. Open a separate business bank account

- Simplest option: Ubank, ING, or any fee-free account — just keep it separate from personal

- All client payments in, all business expenses out. Makes GST and tax tracking straightforward.

## 1.2  Tools & Infrastructure

Keep this lean. You need a booking tool, a payment tool, and a way to send files. Don’t over-invest before you have clients.

| Tool | Purpose | Recommended Option | Cost |
| --- | --- | --- | --- |
| Booking / scheduling | Clients self-book Direction Calls | Acuity Scheduling or Calendly | Free tier to start |
| Online payment | Collect payment before sessions | Stripe (via Acuity) or Square | 2-3% per transaction |
| Intake forms | Collect client info before sessions | Typeform or Google Forms | Free to start |
| File delivery | Send mood boards, summaries, PDFs | Google Drive shared folders | Free |
| Mood board creation | Polished visual design boards | Canva Pro | ~$20/month — worth it |
| 3D visualisation | 3D bathroom mock-ups | Outsource via Upwork or Fiverr | ~$50-150 per render |
| Invoicing | Professional invoices with record | Xero or Wave (free) | Wave is free to start |
| CRM / client notes | Track every client detail | Notion (free) or a simple spreadsheet | Free |
| Communication | Client correspondence | Your business Gmail | Included above |

## 1.3  Core Templates to Build Before Launching

These are the deliverables that make Ritual & Stone look and feel like the premium service it is. Build all five before you take a single paid client.

- High priority. Intake form

- Current bathroom photos (mandatory), dimensions, Pinterest/inspiration images

- Style preferences, must-haves, dealbreakers, budget range, renovation timeline

- What’s frustrating them most right now

- Note: the question ‘what’s frustrating you most’ is worth its weight in gold — it tells you exactly how to open the consultation

- High priority. Mood board template

- Create 1 beautifully branded Canva template you can adapt per client

- Include: palette, tiles, tapware, texture details, lighting feel, atmosphere

- Should feel like something worth printing and framing

- High priority. Client terms & disclaimer

- Scope of services clearly stated (design direction only — not construction, builder coordination, or project management)

- Payment terms: 100% upfront before session

- Revision policy and what’s included vs. chargeable

- Note: your terms don’t need to be aggressive — they need to be clear. Clarity is kindness.

- Medium priority. 3D visualisation outsource brief

- A template you send to your 3D render freelancer

- Include: client-provided photos, dimensions, tile/tapware/fixture selections, desired mood

- Source and trial 1-2 3D render freelancers via Upwork before offering this to clients

- Medium priority. Product shopping list template

- Branded PDF template with product name, supplier, approximate price, notes

- Clear disclaimer: quantities, availability, and final ordering are client responsibility

## 1.4  Portfolio Proof

You cannot sell luxury without showing luxury. You need 2-3 bathroom concepts in your visual language before soft launch — even if they are concept boards, not real projects.

- Create 2-3 sample Ritual & Stone bathroom mood boards in Canva

- Style variations: coastal stone, warm earthy, modern zen

- These are your portfolio starting point and can be used on Instagram

- Label them clearly as ‘concept direction’ rather than completed projects

- Ask 1-2 trusted contacts if you can use a bathroom project from your Create & Foster years for portfolio

- Even an older real project beats a concept board — if you have beautiful photos, use them

# 2. The Phase Roadmap

Each phase is defined by a revenue trigger and a readiness check — not just a date on a calendar. When the trigger is met and you feel steady, you move forward. When it’s not, you stay put and do the work.

The phases are designed around your life: still at Beaumonts on Mondays-only, pregnancy timeline, postpartum recovery, and eventual freedom. You don’t have to rush any of this.

| PHASE 0a Digital Foundation | Advance trigger: ABN confirmed. Business name registered. Domains + handles secured. Business email live. | Revenue target $0 |
| --- | --- | --- |

June – August 2026. No workspace needed — everything here can be done from any device, wherever you are. No public launch. No client pressure.

- This is your digital identity month. Nobody knows Ritual & Stone exists yet — and that's fine.

- Focus only on Section 1.1 — Legal & Administrative Foundation. The rest waits until you're in the house.

- The goal is not revenue — it’s readiness. You should feel ready to take a paying stranger by end of June.

- After August 31st, Phase 0b begins: move in, settle, upgrade your computer, and build everything else — tools, templates, mood boards. Target: everything ready by end of November.

December 2026 is intentionally quiet. No launch, no pressure. Enjoy your new home and let January do the heavy lifting — it's one of Perth's strongest months for renovation planning.

| PHASE 0b Setup & Build | Advance trigger: All 5 templates built. Tools live. Mood boards done. Dry-run complete. You feel ready. | Revenue target $0 |
| --- | --- | --- |

September – November 2026. You're in the house. Now build the machine properly.

- Upgrade your computer — Canva, video calls, and mood board work need a solid setup

- Set up your workspace: a dedicated desk, good lighting, a space that feels like Ritual & Stone

- Work through Section 1.2–1.4 of this document: tools, templates, portfolio

- Do a full dry-run of the client journey before December — book yourself, complete the intake form, run a mock call, send the deliverable

- Pre-schedule December Instagram content so the brand stays warm while you rest

| PHASE 1 Proof of Concept | Advance trigger: 2+ paying strangers. At least 1 unsolicited positive response. You know the call flow works. | Revenue target $1,000 – $2,000/month |
| --- | --- | --- |

January – February 2027 — Perth only. Direction Calls only. Add-ons available. January is one of Perth's strongest months for renovation planning — ride that wave.

- Soft launch. This is a whisper, not a shout.

- Services: Bathroom Direction Call ($150) + Product Shopping List ($100) + Trade Contact List ($50)

- How to find clients: tell 5-10 people in your network what you’re doing; one referral leads to another

- Instagram: 3-5 posts showing the Ritual & Stone aesthetic — not sales, just identity

- Set up your booking link and intake form live on this date

- Capacity: 4-6 Direction Calls per month max

Your goal this phase is simple: prove that a stranger will pay $150 for 75 minutes of your brain. Once you have proof, everything else becomes easier to believe.

| PHASE 2 Validation | Advance trigger: Revenue $2,500+/month for 2 consecutive months AND at least 25% of Tier 1 clients buying an add-on. | Revenue target $3,000 – $5,500/month |
| --- | --- | --- |

March – May 2027 — Perth. Add Selection Sessions. Introduce Design Plans.

- Now add: Bathroom Selection Session ($300) and Concept Plans + 3D Mock-up add-on ($300)

- Start offering Tier 3 Bathroom Design Plans ($1,100) to clients who are clearly ready for more

- Key metric to watch: upgrade rate. Are Tier 1 clients upgrading or buying add-ons? If yes, the business has a natural funnel.

- Begin building your supplier knowledge base (key tile, tapware, and fixture suppliers in Perth)

- Post more consistently on Instagram — 3x per week. Start showing process, not just aesthetics.

- Beaumonts consideration: if revenue hits $3,500+/month for 2 months, begin thinking about reducing hours

| PHASE 3 Controlled Growth | Advance trigger: Revenue $3,500+/month for 2 consecutive months. Beaumonts hours decision made. | Revenue target $2,500 – $4,500/month |
| --- | --- | --- |

Mid 2027. Hold steady and protect your energy. This is a sustainability phase, not a growth phase.

- This is a sustainability phase, not a growth phase. Hold steady.

- Only take what you can do well and without strain. A bad client experience now costs you more than a missed booking.

- Set up a waitlist system: ‘We’re currently booking for [date]’ — this signals demand and maintains momentum

- Prepare your postpartum pause message — you’ll need it ready to go

- Make the Beaumonts decision if the numbers support it (refer to Section 5: Revenue Math)

A note on life: this business is designed to pause gracefully if you ever need it to — for any reason, at any time. A waitlist holds your reputation while you rest. Ritual & Stone will still be here when you're ready to return.

| PHASE 4 Rest & Hold | Advance trigger: Health is the only metric. Waitlist maintained. Business exists but pauses. | Revenue target $0 – $1,000/month |
| --- | --- | --- |

January – March 2027 — Birth and postpartum. Closed or near-closed.

- You are not open for new clients in this phase. Your only job is to recover and be present.

- If you want to take the occasional Direction Call and it genuinely feels easy and enjoyable, that’s fine — but make it opt-in, not obligatory.

- Maintain your Instagram with evergreen content you pre-schedule before January

- Existing clients are on hold or handed off with warmth and clear next steps

A business that pauses intentionally and returns with full energy is stronger than one that limps through and burns out. Ritual & Stone will be here in April.

| PHASE 5 Relaunch | Advance trigger: $5,000+/month for 2 consecutive months. Feel genuinely ready to grow. | Revenue target $5,000 – $8,000/month |
| --- | --- | --- |

April – June 2027 — Postpartum rebuild. Full package ladder returns.

- Full relaunch with all tiers: Direction Call, Selection Session, Design Plan, Full Design Plan

- Return to Instagram with a soft re-introduction — honest, warm, and on brand

- Consider introducing your first waitlist pricing tier (prioritised access for returning clients)

- Start thinking about what scaling looks like for you personally. More clients? Higher prices? Or both?

| PHASE 6 Growth & Freedom | Advance trigger: $7,000+/month gross for 3 consecutive months + 3-6 month buffer saved. | Revenue target $7,000 – $12,000+/month |
| --- | --- | --- |

July 2027 onward — Beaumonts exit. Interstate expansion. The dream, fully alive.

- If the revenue triggers are met, give notice at Beaumonts. You built the bridge; now cross it.

- Open to interstate clients: Sydney, Melbourne, and Brisbane are natural next markets (English-speaking, high-spend)

- Price review: Tier 3 increases to $1,400 and Tier 4 increases to $3,200 in Phase 6

- Consider introducing a membership or retainer element — e.g. an annual ‘Sanctuary Review’ call

- International expansion: Singapore, UK, UAE (expat communities with high bathroom renovation spend) — addressed separately in the Business Bible

# 3. The Client Experience Blueprint

This is the heart of what makes Ritual & Stone different. Every competitor offers design advice. You are going to offer an experience. The difference is felt, not described.

Your north star: the client should feel like this is personal, not transactional. That starts at the very first message they send you and carries through to the last file they receive.

## 3.1  The Touchpoints

Every single interaction is a touchpoint. Below is the full map of what the client experiences and what Ritual & Stone does at each step to make it feel genuinely personal.

| Touchpoint | What the client feels | What you do |
| --- | --- | --- |
| First enquiry / DM | Am I going to be taken seriously here? | Respond within 24 hours. Use their first name. Reference something specific they mentioned. Never send a generic reply. |
| Booking confirmation | Okay, this feels professional | Automated confirmation that is warm and specific — includes what to expect, how to prepare, and a line of genuine excitement about their project |
| Intake form | They actually want to know about ME | Questions that go beyond dimensions — ask what their bathroom feels like right now, and what they wish it felt like |
| Pre-call reminder | This person is organised and has thought about me | A warm reminder email 24-48hrs before, with a reminder of what to have ready and a tone that feels calm and human |
| The call itself | I feel heard. This is not a conveyor belt. | Begin with their pain point (from the intake form). Stay curious. Summarise back to them before pivoting. Don’t rush. |
| Post-call delivery | This is more than I expected | Deliver before the promised deadline. Include a brief personal note. Name the specific thing you loved about their project. |
| The upgrade moment | This doesn’t feel like being sold to | Frame upgrades as a natural continuation, not a pitch: ‘Given what you’ve told me, I think you’d get the most value from...’ |
| Project close-out | I want to work with her again | Send a warm close-out email with next steps. Ask one question: ‘Is there anything else you needed that we didn’t cover?’ |

## 3.2  The Details That Build Trust

These are the small things that collectively make the experience feel genuinely bespoke. None of them cost you money — they cost you attention.

- Remember what they told you in the intake form and reference it on the call without prompting

- Never say ‘Does that make sense?’ — say ‘What questions do you have?’ (it invites not corrects)

- In your post-call email, reference one specific, unexpected detail from the conversation

- Deliver files in a named, organised folder — not a jumbled email attachment

- If their project excites you, say so — genuine enthusiasm is felt and remembered

- If they message with a question after the engagement, answer it — even briefly. It costs you 2 minutes and builds loyalty for life.

## 3.3  Your Brand Voice in Writing

This applies to every email, DM, caption, and document Ritual & Stone puts into the world.

| Instead of this... | Say this... |
| --- | --- |
| Please find attached your mood board | Your mood board is ready — I’ve put a note inside about why I made the choices I did |
| Payment must be received prior to the session | To secure your spot, payment is due before we meet — you’ll receive a simple invoice link |
| I offer a range of packages to suit your needs | Here’s what I think would actually help you most, based on what you’ve described |
| Thank you for your enquiry | Thank you for reaching out — your project sounds like something I’d genuinely love to work on |
| Please complete the intake form | Before we meet, I’d love to know a bit more about your bathroom and what you’re hoping to feel when you’re in it |

# 4. Your First 30 Days — The Foundation Sprint

This is the most important month of Ritual & Stone’s existence. Everything you build here will be the infrastructure you run on for the next 2 years. Do not skip steps. Do not rush past them.

You only get to build the foundation once. Build it as if you’re building it for the business you want to have in 3 years — not just the one that launches in July.

## Week 1 (This Week)

Legal & identity. The things you need to do first because everything else depends on them.

- Check ABN status or apply at abr.business.gov.au

- Search ‘Ritual and Stone’ on asic.gov.au and ipaustralia.gov.au

- Register the business name on ASIC if available (~$39)

- Register ritualandstone.com.au and ritualandstone.com

- Claim @ritualandstone on Instagram and Pinterest

- Set up Google Workspace (business email: hello@ritualandstone.com.au)

- Open a fee-free business bank account (Ubank or ING)

## Week 2

Tools & booking infrastructure.

- Set up Acuity Scheduling (or Calendly) with your Beaumont-safe availability

- Connect Stripe to Acuity so payment is collected at booking

- Build your intake form in Typeform or Google Forms

- Set up Wave or Xero for invoicing

- Create a simple Notion or Google Sheet client CRM to track every client and their details

- Set up a Google Drive folder structure: one folder per client, shared with client at close-out

## Week 3

Templates & deliverables.

- Build the branded mood board template in Canva Pro

- Draft client terms and disclaimer document

- Create the 3D outsource brief template

- Create the product shopping list template

- Write your booking confirmation email and pre-call reminder email

- Write your post-call delivery email template

## Week 4

Portfolio & soft launch prep.

- Create 2-3 sample bathroom mood boards (your Ritual & Stone visual language)

- Tell 5-10 trusted people what you’re launching in July

- Set up Instagram profile with bio, link, and 3-5 initial posts

- Do a full dry-run of the client journey: book yourself, complete intake, run a mock call, send the deliverable

- Source and brief a 3D render freelancer on Upwork or Fiverr for a test render

# 5. Revenue Math, Simplified

You don’t need to hit $7,000 in month one. You need to hit the trigger for the next phase. Here’s what that actually looks like on a Monday.

## What One Monday Can Earn You

| Service | Rate | Mondays (one per week) | Monthly (4 Mondays) |
| --- | --- | --- | --- |
| Direction Call × 2 | $300 | $300 | $1,200 |
| Selection Session × 1 | $300 | $300 | $1,200 |
| Shopping List add-on × 2 | $200 | $200 | $800 |
| Design Plan × 0.5 (bi-weekly) | $550 | $550 | $1,100 |
| Total (realistic Phase 2 Monday) | — | $1,350 | $5,300 |

You don’t need to fill every slot every Monday to build a real business. 2 Direction Calls + 1 upgrade per Monday gets you to $4,000+ a month.

## Phase Revenue Triggers at a Glance

| Phase | Trigger to advance | Revenue signal |
| --- | --- | --- |
| 0a → 0b | Digital identity secured. Handles claimed. Email live. | $0 (readiness, not revenue) |
| 0b → 1 | All templates built. Tools tested. Dry-run done. Workspace ready. | $0 (readiness, not revenue) |
| 1 → 2 | 2+ paying strangers. 25%+ add-on rate. | $1,500+/month — target Feb/Mar 2027 |
| 2 → 3 | Consistent upgrade conversions. 2 months stable. | $2,500+/month for 2 months |
| 3 → 4 | Baby is coming. Wind down intentionally. | Anything you can do comfortably |
| 4 → 5 | You’re ready to return. Energy is real. | $0 (readiness, not revenue) |
| 5 → 6 | Consistent and sustainable. | $5,000+/month for 2 months |
| Beaumonts exit | You’ve proven this works and have a buffer. | $7,000+/month for 3 months + savings |

# 6. What To Do First

If you close this document right now and have time for only one thing today, make it this:

Go to abr.business.gov.au and confirm your ABN is active. Then search ‘Ritual and Stone’ on ASIC. That’s step one. Everything else is built on that.

And if you have a full Monday in front of you and want to move fast, the order is:

| Priority | Action | Time needed |
| --- | --- | --- |
| 1 | ABN check + business name registration on ASIC | 30 minutes |
| 2 | Domain registration (ritualandstone.com.au + .com) | 15 minutes |
| 3 | Claim @ritualandstone on Instagram and Pinterest | 10 minutes |
| 4 | Set up Google Workspace (business email) | 30 minutes |
| 5 | Open business bank account | 20 minutes |
| 6 | Set up Acuity with your availability and Stripe payment | 1-2 hours |
| 7 | Build the intake form in Typeform | 1 hour |
|  | End of Week 1 complete. |  |

This is your business, Ced. It’s already more real than most people’s ever get.

Now go register the name.